## Instructions
Using the Status tracker
At the end of each week, update the status of all activities completed during the week
The status tracker shown in this worksheet is an example tracker (values filled are during the middle of the week)
Fill in hours spent on each activity during the current week
If 5 team members each spent an hour, that counts as 5 hours
Fill in time for activities not fully completed ("ongoing") as well, then update these values during following weeks
During the planning phases, identify the activities to be done during each week
If you spend time on an activity not listed in the tracker, add the activity and list actual hours (need not fill in estimated hours if you didn't estimate it up front)
For new activities, identify the type of activity - documentation, coordination, estimation etc.
At the end of each week, plan ahead for the following week
Identify people responsible for each activity
Estimate the hours needed for the activity
PROJECT NUMBER | (Fill your Project Number here)
PROJECT NAME | (Fill your project name here)
PROJECT MENTOR (sponsor) | (Put your Project Mentor (sponsor) name here)
TEAM MEMBERS | Team Mamber Name 1
Team Member Name 2
Team Member Name 3
Team Member Name 4
Team Member Name 5

## Status
PROJECT NUMBER | 46
PROJECT NAME | Virtual Power Plant
PROJECT MENTOR (sponsor) | (Put your Project Mentor (sponsor) name here)
Activity Name |  | Responsible | Estimated Team Hours | Actual Hours | Status | Comments | Estimation error | Estimation error %
See Instructions sheet for usage
Week 1 (January 16- January 21)
Fix meeting with client | Coordination | Eshwar | 0.5 | 0.3 | Done |  | 12 | 4000
Read client provided project docs | Preparation | Shlok, Aditya | 4 | 4 | Done |  | 0 | 0
Client meeting | Coordination | Hiten | 0.5 | 0.5 | Done |  | 0 | 0
Research existing technology | Preparation | Monosij | 1.5 | 1.5 | Done |  | 0 | 0
Decide and Assign Work | Preparation | Eshwar | 1 | 0.6 | Done |  | 0.4 | 66.6667
Team Meeting | Coordination | Monosij | 1 | 2 | Done |  | -1 | 50
Week 2 (January 22 - January 28)
Learn basic Rust | Preparation | Monosij | 2 | 2 | Ongoing |  | 0 | 0
Run VTN Server | Testing | Hiten, Aditya, Shlok, Monosij | 4 | 8 | Ongoing
Familiarise with ADR protocol | Preparation | Aditya, Shlok, Hiten | 3 | 4 | Done |  | -1 | 25
Develop questions for requirements elicitation | Documentation | Shlok | 1 | 1 | Done |  | 0 | 0
Make basic code and run VEN client node | Development | Hiten, Aditya, Shlok, Monosij | 6 | 4 | Ongoing |  | 2 | 50
Team Meeting | Coordination | Shlok | 1 | 1 | Done |  | 0 | 0
Status tracker | Documentation | Hiten | 1 | 1 | Done |  | 0 | 0
Find alternate technologies and projects | Design | Eshwar | 1 | 1 | Done |  | 0 | 0
Develop rough project synopsys | Documentation | Aditya | 1 | 1 | Done |  | 0 | 0
Week 3 (January 29 - February 4)
Prep questions for meet | Preparation | Monosij, Shlok, Aditya | 2 | 2.5 |  |  | -0.5 | 20
Run VTN Server | Testing | Hiten, Aditya, Shlok, Monosij | 3 | 4 | Ongoing
Week 4
Week 5
Week 6
Note on C5: SE: The person responsible for ensuring completion, not necessarily all the people doing it
Note on G5: swami: Insert your own comments
Note on H5: SE: This field is updated automatically