## Export Summary
This document was exported from Numbers. Each table was converted to an Excel worksheet. All other objects on each Numbers sheet were placed on separate worksheets. Please be aware that formula calculations may differ in Excel.
Numbers Sheet Name | Numbers Table Name | Excel Worksheet Name
Instructions
| Table 1 | Instructions
Status
| Table 1 | Status

## Instructions
Using the Status tracker
At the end of each week, update the status of all activities completed during the week
The status tracker shown in this worksheet is an example tracker (values filled are during the middle of the week)
Fill in hours spent on each activity during the current week
If 5 team members each spent an hour, that counts as 5 hours
Fill in time for activities not fully completed ("ongoing") as well, then update these values during following weeks
During the planning phases, identify the activities to be done during each week
If you spend time on an activity not listed in the tracker, add the activity and list actual hours (need not fill in estimated hours if you didn't estimate it up front)
For new activities, identify the type of activity - documentation, coordination, estimation etc.
At the end of each week, plan ahead for the following week
Identify people responsible for each activity
Estimate the hours needed for the activity
PROJECT NUMBER | 46
PROJECT NAME | Virtual Power Plant
PROJECT MENTOR (sponsor) | (Put your Project Mentor (sponsor) name here)
TEAM MEMBERS | Eshwar Sriramoju
Hiten Garg
Aditya Shankar
Monosij Roy
Shlok Sand

## Status
PROJECT NUMBER | 46
PROJECT NAME | Virtual Power Plant
PROJECT MENTOR (sponsor) | (Put your Project Mentor (sponsor) name here)
Activity Name |  | Responsible | Estimated Team Hours | Actual Hours | Status | Comments | Estimation error | Estimation error %
See Instructions sheet for usage
Week 1 (January 13- January 19)
Fix meeting with client | Coordination | Eshwar | 0.5 | 0.3 | Done |  | 12 | 4000
Read client provided project docs | Preparation | Shlok, Aditya | 4 | 4 | Done |  | 0 | 0
Client meeting | Coordination | Hiten | 0.5 | 0.5 | Done |  | 0 | 0
Research existing technology | Preparation | Monosij | 1.5 | 1.5 | Done |  | 0 | 0
Decide and Assign Work | Preparation | Eshwar | 1 | 0.6 | Done |  | 0.4 | 66.6667
Team Meeting | Coordination | Monosij | 1 | 2 | Done |  | -1 | 50
Week 2 (January 20 - January 26)
Learn basic Rust | Preparation | Monosij | 2 | 2 | Ongoing |  | 0 | 0
Run VTN Server | Testing | Hiten, Aditya, Shlok, Monosij | 4 | 8 | Ongoing
Familiarise with ADR protocol | Preparation | Aditya, Shlok, Hiten | 3 | 4 | Done |  | -1 | 25
Develop questions for requirements elicitation | Documentation | Shlok | 1 | 1 | Done |  | 0 | 0
Make basic code and run VEN client node | Development | Hiten, Aditya, Shlok, Monosij | 6 | 4 | Ongoing |  | 2 | 50
Team Meeting | Coordination | Shlok | 1 | 1 | Done |  | 0 | 0
Status tracker | Documentation | Hiten | 1 | 1 | Done |  | 0 | 0
Find alternate technologies and projects | Design | Eshwar | 1 | 1 | Done |  | 0 | 0
Develop rough project synopsys | Documentation | Aditya | 1 | 1 | Done |  | 0 | 0
Week 3 (January 27 - February 2)
Prep questions for meet | Preparation | Monosij, Shlok, Aditya | 2 | 2.5 |  |  | -0.5 | 20
Run VTN Server | Testing | Hiten, Aditya, Shlok, Monosij,Eshwar | 3 | 4 | Done
Client meeting | Coordination | Aditya | 1 | 1.5 | Done |  | -0.5 | 33.3333
Team Meeting | Coordination | Hiten,Shlok, Eshwar | 3 | 3 | Done
Research on Drives & Drives Company | Preparation | Hiten, Monosij,Shlok,Eshwar | 3 | 3 | Done
Developed Project Synopsis | Documentation | Shlok | 1 | 1 | Done
Developed Project Plan | Documentation | Aditya | 1 | 1 | Done
Status tracker | Documentation | Hiten | 1 | 1 | Done
Minutes of Meeting | Documentation | Eshwar | 1 | 1 | Done
Week 4 (February 3 - February 9)
Team Meeting | Coordination | Hiten | 2 | 2 | Done | Discussion on project rescoping according to the requirement document sent by the client | 0 | 0
Client meeting | Coordination | Shlok | 1.5 | 1 | Done |  | 0.5 | 50
Software Structure Design | Documentation | Hiten, Aditya, Shlok, Monosij,Eshwar | 5 | 6 | Done |  | -1 | 16.6667
Decide and Assign Work | Preparation | Aditya | 1 | 1 | Done |  | 0 | 0
Week 5 (February 10 - February 16)
Team Meeting | Coordination | Aditya, Monosij | 2 | 2 | Done |  | 0 | 0
Run VEN | Testing | Shlok, Hiten | 2.5 | 2.5 | Done |  | 0 | 0
Improve software structure design | Design | Aditya, Shlok, Eshwar, Hiten, Monosij | 5 | 5 | Done |  | 0 | 0
Week 6 (February 17 - February 23)
SRS | Documentation | Eshwar, Monosij, Hiten | 2 | 2 | Done |  | 0 | 0
Basic repo and functionality | Design | Aditya, Shlok | 3 |  | Ongoing
Team Meeting | Coordination | Aditya, Eshwar | 2 | 1.5 | Done |  | 0.5 | 33.3333
Client meeting | Coordination | Aditya, Shlok, Eshwar, Hiten, Monosij | 2 | 2 | Done |  | 0 | 0
Reading specification | Preparation | Aditya, Shlok, Hiten | 3 | 2 | Done |  | 1 | 50
Testing Libraries | Testing | Hiten, Monosij,Shlok,Eshwar | 4 | 3 | Done |  | 1 | 33.3333
Fixing VTN Server | Testing | Aditya, Shlok, Eshwar, Hiten, Monosij | 4 | 3 | Ongoing |  | 1 | 33.3333
Setting up vtn server on Virtual Machine | Testing | Eshwar, Monosij, Hiten | 3 | 2 | Ongoing |  | 1 | 50
Mom | Documentation | Hiten | 1 | 1 | Done |  | 0 | 0
Week 7 (February 24 - March 2)
Team Meeting | Coordination | Aditya, Eshwar, Hiten, Monosij, Shlok | 1 | 1 | Done |  | 0 | 0
Mom and updating status tracker | Documentation | Monosij | 0.5 | 0.5 | Done |  | 0 | 0
Week 8 (March 3 - March 9)
Team Meeting | Coordination | Aditya, Eshwar | 1 |  | Done
Authentication | Development | Eshwar, Shlok, Monosij | 3 |  | Ongoing
Charging Session | Development | Aditya, Hiten | 3 |  | Ongoing
Payment Processing | Development | Monosij, Eshwar | 3 |  | Ongoing
Mom and updating status tracker | Documentation | Shlok | 1 |  | Done
Week 9 (March 10 - March 16)
Team Meeting | Coordination | Shlok, Hiten | 1 | 1 | Done |  | 0 | 0
Authentication | Development | Eshwar, Shlok, Hiten | 3 | 3 | Done |  | 0 | 0
Charging Session | Development | Eshwar, Hiten, Shlok | 3 | 2 | Done |  | 1 | 50
Payment Processing | Development | Monosij, Hiten, Shlok | 3 | 4 | Done |  | -1 | 25
Mom and updating status tracker | Documentation | Shlok | 1 | 1 | Done |  | 0 | 0
Registration | Development | Eshwar, Shlok, Hiten | 3 | 2 | Done |  | 1 | 50
Client meeting | Coordination | Aditya | 1 | 1 | Done |  | 0 | 0
Testing node.js plugin, finding python implementation of openADR 3.0, setting up server | Preparation | Aditya | 5 | 5 | Done
Week 10 (March 17 - March 23)
Create Presentation | Design | Eshwar, Aditya, Hiten, Shlok, Monosij | 2 |  | Planned
Create UI | Development | Aditya, Hiten, Shlok | 3 |  | Planned
Team Meeting | Coordination | Eshwar | 1 |  | Planned
Client meeting | Coordination | Monosij | 1 |  | Planned
API Creation | Development | Aditya, Hiten, Shlok | 3 |  | Planned